## Slide 1: UCS1405 – SOFTWARE ENGINEERING
Metrics for the requirement model
Dr.K.Madheswari
ASP/CSE

## Slide 2: Learning Objective

## Slide 3: Overview

## Slide 4: Function-Based Metrics
The function point (FP) metric can be used effectively as a means for measuring the functionality delivered by a system
Using historical data, the FP metric can then be used to
(1) estimate the cost or effort required to design, code, and test the software; (2) predict the number of errors that will be encountered during testing; and
(3) forecast the number of components and/or the number of projected source lines in the implemented system

## Slide 5: Function-Based Metrics
Function points are derived using an empirical relationship based on countable (direct) measures of software’s information domain and qualitative assessments of software complexity.
Information domain values are defined in the following manner:
Number of external inputs (EIs)
Number of external outputs (EOs)
Number of external inquiries (EQs)
Number of internal logical files (ILFs).
Number of external interface files (EIFs).

## Slide 6: Function-Based Metrics
To compute function points (FP), the following relationship is used:

## Slide 7: Function-Based Metrics
A target product has 7 simple inputs, 2 average input, and 10 complex inputs. There are 56 average output, 8 simple inquires, 12 average master files, and 17 complex interfaces. Identify the unadjusted function points (UFP). If the total degree of influence for the product is 49 (∑Fi), calculate the number of function points.
7 x 3 +2 x 4+ 10 x6 + 56x 5+ 8x3+ 12x10+17*10= (UFP)

## Slide 8: EARNED VALUE ANALYSIS
The earned value system provides a common value scale for every [software project] task, regardless of the type of work being performed.
The total hours to do the whole project are estimated, and every task is given an earned value based on its estimated percentage of the total.

## Slide 9: EARNED VALUE ANALYSIS
earned value is a measure of progress. It enables you to assess the “percent of completeness” of a project using quantitative analysis rather than rely on a gut feeling.

## Slide 10: EARNED VALUE ANALYSIS
To determine the earned value, the following steps are performed
The budgeted cost of work scheduled (BCWS) is determined for each work task represented in the schedule. During estimation, the work (in person-hours or person-days) of each software engineering task is planned. Hence, BCWSi is the effort planned for work task i.
The BCWS values for all work tasks are summed to derive the budget at completion (BAC). Hence,

## Slide 11: EARNED VALUE ANALYSIS
To determine the earned value, the following steps are performed
3. Next, the value for budgeted cost of work performed (BCWP) is computed. The value for BCWP is the sum of the BCWS values for all work tasks that have actually been completed by a point in time on the project schedule.

## Slide 12: EARNED VALUE ANALYSIS
It is also possible to compute the actual cost of work performed (ACWP). The value for ACWP is the sum of the effort actually expended on work tasks that have been completed by a point in time on the project schedule. It is then possible to compute

## Slide 13: EARNED VALUE ANALYSIS
Example SPI calculation No
Project #1 has a $5,000 budget and is scheduled for 30 days. To date, 50% of the work is complete, which is in line with the project’s schedule.
To calculate your project’s SPI performance, the formula is:
Schedule Performance Index (SPI) = Earned Value (EV) / Planned Value (PV)
SPI = EV / PV
if the SPI calculation yields a value that is:
Greater than 1: The project is ahead of schedule.
Less than 1: The project is behind schedule.
Equal to 1: The project is on schedule.
Planned Value (PV) = Planned % Complete x Budget at Completion (BAC)
PV = % Planned Complete x BAC

## Slide 14: EARNED VALUE ANALYSIS
Example SPI calculation No
Project #1 has a $5,000 budget and is scheduled for 30 days. To date, 50% of the work is complete, which is in line with the project’s schedule.
Planned Value (PV) = Planned % Complete x Budget at Completion (BAC)
PV = % Planned Complete x BAC
PV=50 % x $ 5000
PV=$2500
EV = % Actual Complete x BAC
EV=50 % x $ 5000
EV= $2500
SPI = EV / PV=$2500/$2500=1.0

## Slide 15: Example
Solve the given problem to determine cost and schedule performance index. Suppose you have a budgeted cost of a project at $900,000. The project is to be completed in 9 months. After a month, you have completed 8 percent of the project at a total expense of $200,000. The planned completion should have been 12 percent. Calculate Schedule performance Index (SPI), schedule variance (SV), cost performance Index (PI), and cost variance (CV).

## Slide 16: Solution
BAC = $900,000
AC = $200,000
Planned Value = Planned Completion (%) * BAC = 12% * $900,000 = 108000
Earned Value = Actual Completion (%) * BAC = 8% * $900,000 = $72000
Cost Performance Index = EV / AC = $72000 / $200,000 = 0.36
SPI= Earned Value / Planned Value = $72000/ 108000=0.66

## Slide 17: Solution
Schedule Variance (SV) = Earned Value (EV) – Planned Value (PV)
Cost variance = earned value - actual cost.